**Task 7: Timeline**

Catherine L Hurt

Old Dominion University

HMSV 440W: Program, Development, Implementation, & Funding

March 17, 2024

**Timeline**

To Do:

* April 1
  + Meeting scheduled with Grace Aguilar (Executive Director) and Hayley Jones (Program Director – Greater Lynchburg) to discuss the evaluation.
    - Talking Points:
      * The evaluation will take about approximately three weeks to complete.
      * Stakeholder involvement will be at a medium level. I would appreciate their feedback on survey questions and assistance in sending out the surveys to program participants and parents who would like to be involved.
      * Also, I will need five coaches who would like to participate in 30-minute interviews.
* April 2 – 4
  + Email Hayley Jones survey/interview questions for review and receive feedback to make appropriate changes.
* April 5
  + Email participant and parent surveys to Hayley Jones to send to parents/caregivers.
* April 8 – 9
  + 10:00 AM – 4:30 PM Interviews
    - 10:30 AM Staff Interview 1
    - 11:30 AM Staff Interview 2
    - 12:30 PM Staff Interview 3
    - 1:30 PM Staff Interview 4
    - 2:30 PM Staff Interview 5
    - 3:00 PM – 4:00 PM – Collect returned surveys from Hayley
* April 10 – 18
  + Collect any additional surveys
  + Organize and analyze data
  + Complete findings and discuss with GOTR Executive Director and Greater Lynchburg Director
  + Send Thank You cards.