## Slide 1: Improved Transition of Richmond City Foster Care Aging into Independent Living Program Plan
Kayla Jones
08/04/2021
MPH 661

## Slide 2: Executive Summary
The goal of this community-based program is to better understand the needs of youth as they age out of the foster care system and provide them the best resources available to successfully thrive in independent living.
This program works to ensure each foster child does not feel alone and has someone in the foster care system they can relate to, along with a social worker they can confide in.
Focusing in on providing a mental health specialist during independent living will also guarantee that each individual can thrive living in a society that is new to them.
This program should ultimately make each foster child feel that they have an overwhelmingly large support system through their peers they have met along the way in the system and the well trained encouraging social workers.

## Slide 3: Statement of the Health Problem
In 2016, Virginia Department of Social Services (VDSS) implemented Fostering Futures, the extension of foster care to age 21.
Since then, the average rate of entry into Fostering Futures is approximately 50% of all youth turning 18 in foster care. (Virginia’s five year state plan for child and family services, 2019).
As of March 2021, out of 215 children in the Richmond City foster care system, 37 (17.2%) are age 19 and over and 48 (22.3%) are age 16-18 (Foster Care (FC) Related Reports, 2021).

## Slide 4: Statement of the Health Problem
The health problem is the transition of late teens to early twenties from foster care to adult independent living in the Richmond City foster care system.
This is a problem because transitioning from a group home setting to independent living without family can be mentally and physically overwhelming.
Virginia ranks near the worst in the nation for the percent of foster youth who age out of the system. 21.2% of Virginia’s foster youth will turn 18 and never been adopted (Turner-Miller, 2021).

## Slide 5: Health Effects
The health effects of foster care children entering independent living ill-prepared is astronomical. Mental health and complex trauma following them from a child into adulthood has a significant impact.
“A disturbing 21.1% of foster care children in Virginia will age out and become legal adults with little or no social or emotional support. While about 20% of the general population has significant mental health issues, up to 80% of children in the Virginia foster care system have significant mental health issue. Among foster youth, these problems commonly include post-traumatic stress disorder (PTSD), major depression, dysthymia, mania and hypomania, psychotic disorders, social phobias, panic disorder, anxiety, drug or alcohol dependence, and bulimia” (Turner-Miller, 2021).

## Slide 6: Human Trafficking Targets
Another concern for foster care children is they are at greater risk for human/child trafficking. VDSS continues to identify, track, and serve victims of child trafficking as another population at the greatest risk of maltreatment. Based on the most recent case type recorded for each client, 56% were involved in foster care, 17% in CPS (Child Protective Services) ongoing, and 3% in dual CPS ongoing and foster care (Virginia’s five year state plan for child and family services, 2019).

## Slide 7: Health Care
Youth in foster care who had an open case and were receiving Virginia Medicaid at the age of 18 are eligible for Medicaid up to age 26 (Virginia’s five year state plan for child and family services, 2019). After that, these young adults are on their own in trying to understand the health care system of finding health insurance for themselves, or why they even need it.
Knowing how to budget, prepare for college, build credit, and find healthcare for yourself once you age out are all important life skills that need to be taught to foster care children before they are sent to independent living so that they do not make poor about their health and wellbeing.

## Slide 9: Program Description
The program will closely follow the evidence-informed community-based model that is shown in LifeSet that began in 1999 and is currently thriving in many states.
The idea for the Richmond City program is to continue the community-based model and work with best practices values in mind. Each foster child, starting around age 16, will be paired with a social worker and a group home “buddy” based on a questionnaire about themselves, life goals, and family history to make sure all three are a good match for each other.
The foster care youth will work with the social worker and keep in contact with their buddy from the group home for at least a year into independent living transitioning and can be extended if deemed necessary by the social worker. The regular contact for the first year can include video chat, phone call, or in person meeting at least biweekly, just some form of verbal contact to help ensure each individual is transitioning well. The program will also have monthly group gatherings for multiple youth from the group home to meet again and discuss how their transition is going.

## Slide 10: Program Description
The program will promote a support group, offer life skill information, obtain safe housing guidance, education assistance, employment aid, and tools to help each individual succeed in life and know they are not alone.
The program will also provide a mental health specialist to provide mandatory therapy sessions every three months to help with any overwhelming stresses in life during the adjustment period.
These policies should help each foster child feel more individualized care, assistance, and communication as they face a change in their life. Having encouraging social and emotional support from the system and others who have been in foster care is critical to promote positive mental health wellbeing.

## Slide 11: Program Description
On the Socioecological model this program would fall under the interpersonal level to promote positive and health relationships between the specialists and the youth they are working with to function in society. It would also fall under community factors by the specialists helping the youth learn to adapt to independent living, learning how to function in society, and be a part of society.

## Slide 12: Goal and Objectives
Goal: Improve the mental health care quality, accessibility, and effectiveness of support that service Richmond City foster care youth to help them adapt better into independent living.
Objectives:
Provide a mental health therapist for the first 12 months for foster care youth transitioning into independent living to help discuss any underly mental health issues then re-evaluate if continued care is needed on an individual basis.
Have the mental health specialists and all trained professionals paid for through government grants from the state.
Improve the mental health status in adults with a foster care background within the next 10 years with the addition of mental health specialists in the program.

## Slide 13: Implementation
Program Activities | Output | Anticipated Outcomes | Longer-term Goal
The community-based program will work with the foster care youth getting ready to age out of the system in Richmond, Virginia Each foster child will be paired with a social worker and buddy based on a questionnaire about themselves, life goals, and family history The foster care child will work with this social worker and buddy within their last couple years in foster care and at least the first year into independent living transition as needed by the social worker | The target number for this program is 100 foster care children, age 16 and up in Richmond City | A better support system for the older aged foster care youth This will be measured through pre- and post- surveys asking the child about their current support system An improvement in the mental health status of foster care youth This will be measured during the mental health sessions; an intake and outtake form will be filled out asking how each child is feeling that day and why | A change in the stigma put on foster care youth that is seen in society A foster care child feeling the same individualized care, assistance, and communication as a child living in a home with a family would receive Positive mental health effects from having a mental health therapist to discuss childhood trauma

## Slide 14: Implementation
Program Activities | Output | Anticipated Outcomes | Longer-term Goal
The program will also have group gatherings of days and times for multiple foster care youth that have transitioned into adult hood to meet for a social gathering The program will promote a support group, offer life skill information, obtain safe housing guidance, education assistance, and employment aid The program will provide a mental health specialist group to provide therapy sessions to all foster care youth as they transition into independent living | The target number for this program is 100 foster care children, age 16 and up in Richmond City | An improvement in the transitional stage from foster care living to independent living This will be measured by the amount of foster care youth that are engaged in bettering themselves, either in higher education, a trade school, being an entrepreneur, or working a steady job | An increase in social and emotional support from the system and from others in foster care Learning lifelong skills to better themselves as a member in society and have the same advantages as others would

## Slide 15: Evaluation Design
The evaluation design for this program is done using bivariate analysis and through pre- and post-test measurement. Bivariate analysis: Is there a difference in mental health status on the Richmond City independent living foster care youth after receiving professional mental health therapy and having a strong support system three years after the program?
This is a process indicator type of evaluation because it will assess the implementation process in general, and track and measure what went well, what needs to improve, and how these factors contribute to the success or failure of the program.

## Slide 16: Evaluation Design
Information for this evaluation will be gathered through a pre-test survey every time a child aged 16 and older enters the foster care system in Richmond City asking about their current mental health status, if they have any childhood trauma, if they have a support system, etc. then the same post-test survey will be given as they leave the foster care system each time. This same survey will be given when the youth are in independent living for each session they meet with the mental health specialist – before and after each session.
On the socioecological model this will work on the interpersonal level to improve relationships between the youth and their close circle they are functioning with in society.

## Slide 17: Application of Data Analysis example:
Program goal: Improve the mental health status on the Richmond City foster care youth transitioning to independent living Program population: Richmond City foster care youth aged 16 and up with a focus on those in independent living Intervention: Mental health therapy required every three months for at least the first year during independent living Variable of interest: Better mental health status starting after the first year Evaluation design: O1 X O2 Where: O1 = pre-test survey data X = therapy session O2 = post-test survey data Data collected: Scores on a 1-5 Likert scale ____Survey Results___ Pre-test Post-test Number of independent living youth 117 117 Mean number 2.24 4.11 Data analysis: A correlation graph is used to best show the strength and direction of the relationship between the two variables

## Slide 18: Conclusion
Following these results would recommend on continuing the program as long as it remains effective and continuing to re-evaluate the program yearly. Adjustments should be made as needed per changes in staff, the economy, and finances.
A limitation to this study is that is short term and only done in a local area, a recommendation would be to implement this program and the surveys in multiple random cities to evaluate how well they do in different areas across the United States to help improve the mental health and support system of independent living foster care youth.
The use of this program shows that an improvement in engaging foster care youth and providing better training to social workers can improve the transition of said youth to independent living.
This overall improves the economy by providing individuals who are able to perform in the real world to the best of their abilities and may end up turning around and helping more foster children someday. Having emotional support is imperative to set a solid foundation to build and grow on. Having this program plan to use for the social workers and foster care youth to learn to become a team in care is a win for the community.

## Slide 19: Support Survey for Richmond City Foster Care Youth Aged 16 and Up How old are you? _____ Is this your first foster care location?______   If not, where else have you been located:_________________________________ Are you currently in independent living?_____   If yes, how long have you been independently living:______________________ Is there anything else you would like to me to know?
 | 1 – Strongly Disagree | 2 - Disagree | 3 - Neutral | 4 - Agree | 5 – Strongly Agree
I have experienced past traumatic experiences in my life |  |  |  |  | 
I feel safe where I am living |  |  |  |  | 
I have a good support system |  |  |  |  | 
I feel my voice is being heard |  |  |  |  | 
My cultural background is respected |  |  |  |  | 
I feel prepared to live on my own |  |  |  |  | 
Foster care has helped prepare me for my future |  |  |  |  | 
I have a plan for my future |  |  |  |  | 
I feel my privacy is respected |  |  |  |  | 
I am happy |  |  |  |  | 
I do not feel sad |  |  |  |  | 
I do not feel angry |  |  |  |  | 
I do not feel depressed |  |  |  |  | 
I like my social worker |  |  |  |  | 

## Slide 20: References Foster Care (FC) Related Reports. Foster Care (FC) Related Reports – Virginia Department of Social Services. (2021). https://www.dss.virginia.gov/geninfo/reports/children/fc.cgi LifeSet: The gift of a good start. Youth Villages. (2021, May 24). https://www.youthvillages.org/services/lifeset/ Turner-Miller, R. (2021, June 5). Disparities in Mental Health Care Among Virginia’s Foster Children. Mental Health America of Virginia. https://mhav.org/disparities-in-mental-health- care-among-virginias-foster-children/ Virginia’s five year state plan for child and family services. Commonwealth of Virginia Department of Social Services. (2019, June).https://www.dss.virginia.gov/files/division/dfs/iv_e/state_plans/cfsp_plans/VDSS_CFSP_2 020-2024_9.24.19.pdf